LEE ENTERTAINMENT Wedding Show Prep Kit Cake & Champagne Wedding Show Sunday, April 19, 2026 ──────────────────────────── Abraham Lee · Christian Orlowski · Designer Weddings Victoria Confidential — Internal Use Only

Show Overview Show Name; Cake & Champagne Wedding Show. Date; Sunday, April 19, 2026. Days Away; 32 days — treat as URGENT. Estimated Booths; ~70 vendors. Target Leads; 20+ qualified couples. Target Bookings; 6–7 bookings (based on 33% conversion rate). Key Offer; Eternal Elegance Diamond — Booth Decorated FREE by Designer Weddings Victoria. Offer Deadline; May 30, 2026 — while spots last. Lee Entertainment Team; Abraham Lee (DJ) · Christian Orlowski (Camera & Lead Capture). Backdrop Partner; Designer Weddings Victoria — Linda & Melissa · @designerweddingsvictoria.

01 — THE SHOW-ONLY OFFER

What We're Offering at This Show

This is the single most important element of the booth. Every conversation, every interaction, every piece of signage should point to this offer.

EXCLUSIVE SHOW OFFER Book the Eternal Elegance Diamond Package Get Your DJ Booth Decorated FREE by Designer Weddings Victoria ──────────────────── Book before May 30, 2026 · While spots last Available to DJ Abraham Lee bookings only

Why This Offer Works

- The booth decoration is a tangible, visible, exciting add-on — couples understand and want it immediately

- Designer Weddings Victoria is already at the show — their work is visible right in our booth, making the offer real and credible

- The May 30th deadline creates urgency without pressure — it's about limited availability, not desperation

- It differentiates Abraham's package from every other DJ at the show

- It creates a referral relationship with Designer Weddings Victoria — a vendor partnership that generates future bookings

02 — THE $1,500 GIVEAWAY

Enter to Win — Content Creation Package

The giveaway is the lead capture engine. Every person who enters gives us their contact information and goes into the follow-up sequence. This is not optional — it is the most important conversion tool at the booth.

| THE PRIZE | THE RULES |
| --- | --- |
| Full Wedding Day Content Creation Package Value: $1,500 8 hours of professional on-site video and photo content capture on your wedding day. Only available with DJ Abraham Lee — Eternal Elegance Diamond Package. | Entry via QR code → Lee Entertainment inquiry form Paper backup sign-in sheet available at booth Winner announced: May 1, 2026 Open to couples with a 2026 or 2027 wedding date Winner contacted by email and announced on Instagram |

03 — BOOTH SETUP & DESIGN

What the Booth Looks Like

The booth needs to stop people mid-walk. Every element serves a purpose — attraction, engagement, or conversion.

| ELEMENT | DETAILS & PURPOSE |
| --- | --- |
| Backdrop | Designer Weddings Victoria floral wall — green with white florals. The visual anchor of the booth. Couples stop because it is beautiful. Coordinate updated design details with Linda & Melissa before the show. |
| DJ Booth | Black professional DJ booth with monogram TV on front. TV cycles between: (1) couple name monogram display, (2) Google Reviews highlights, (3) Giveaway slide — $1,500 Content Package. |
| Giveaway Sign | Prominent signage: "Enter to Win — $1,500 Wedding Content Creation Package." QR code leads directly to inquiry form. Winner announced May 1st. While spots last messaging for the booth offer. |
| Music | Live DJ set playing at the booth throughout the show. Upbeat, wedding-appropriate. This creates an energy bubble — people are drawn to the sound. |
| Paper Lead Sheet | Simple clipboard with sign-in sheet. Name, email, wedding date, Instagram handle. Backup for anyone who doesn't scan the QR code. |
| Instagram Follow Station | Small sign: "Get your photo tagged — follow us now @[handle]." Christian invites people to follow before taking their photo so they see it when it posts. |
| Business Cards | Professional Lee Entertainment cards available. Secondary — the QR code and Instagram follow are more valuable. |

04 — CHRISTIAN'S ROLE SHEET

Christian Orlowski — Show Day Responsibilities

Christian is not just the camera person. He is the lead engagement manager. His job is to draw people in, create a moment, capture it, and convert the interaction into a follow and a lead entry.

| TIMING | TASK | HOW TO DO IT |
| --- | --- | --- |
| Setup | Booth setup assist | Help Abraham set up the booth. Ensure the camera is charged, memory cards are clear, and the Instagram follow sign is visible. |
| During Show | Invite couples into the booth | Walk slightly outside the booth. Make eye contact with passing couples. Smile and say: "Come take a photo in front of our backdrop — we're posting them on Instagram today." Do not ask, invite. |
| During Show | Instagram follow first | Before taking the photo say: "Follow us real quick at @[handle] so you get tagged when this posts." Hand them your phone with the profile open. Wait for the follow. Then take the photo. |
| During Show | Take the photo | Take 2–3 shots. Show them the best one immediately. Say: "That one is going up — you're going to look amazing." |
| During Show | Lead capture handoff | After the photo, hand them the clipboard or point to the QR code: "While you're here — enter our giveaway. We're giving away a $1,500 content package. You just have to fill out the form." |
| During Show | Track Instagram follows | Keep a running note of everyone who follows. This is your real-time lead list. |
| During Show | Collect paper sign-ins | Manage the clipboard. Make sure every person who visits fills in name, email, wedding date, and Instagram handle. |
| During Show | Content capture | Capture behind-the-scenes content of Abraham DJing, couples at the booth, and booth atmosphere. This is social media gold. |
| Post Show | Instagram tagging | Within 2 hours of show end — post the best couple photos and tag every handle collected. Stories and feed posts. |
| Post Show | Lead list to Abraham | Hand Abraham the complete paper sign-in sheet and the Instagram follow list before end of day. |

Christian's Script — What to Say Opening invite: "Come take a photo in front of our backdrop — we're posting them on Instagram today and you two are going to look amazing." Instagram follow ask: "Before I take the photo, follow us real quick so we can tag you when it goes up." [Hand them phone with profile open] Giveaway pitch: "While you're here — we're giving away a full wedding content creation package worth $1,500. Just scan this code or sign the sheet. Winner announced May 1st."

05 — BOOTH PREP CHECKLIST

Everything That Needs to Happen Before April 19th

Two Weeks Before — April 5th

| ✓ | TASK | NOTES |
| --- | --- | --- |
| ☐ | Confirm booth details with show organizer — location, size, setup time, load-in access |  |
| ☐ | Confirm backdrop design and setup with Linda & Melissa at Designer Weddings Victoria | @designerweddingsvictoria |
| ☐ | Confirm Christian is available and briefed on his full role sheet | Review this document with him |
| ☐ | Update QR code — confirm it links directly to the inquiry form on the website | Test on multiple phones |
| ☐ | Print paper lead capture sheets — minimum 50 copies | Name · Email · Wedding Date · Instagram Handle |
| ☐ | Design and print Instagram follow sign for the booth | Show @leeentertainment handle clearly |
| ☐ | Design and print giveaway signage — $1,500 prize, QR code, May 1 winner date |  |
| ☐ | Design and print show-only offer signage — Free DJ booth decoration, May 30 deadline | Include Designer Weddings Victoria credit |
| ☐ | Prepare TV display cycle — monogram screen, Google Reviews slide, giveaway slide | Test on booth TV before show |
| ☐ | Confirm music playlist for the show — upbeat, wedding-appropriate, varied | Pre-load and test offline |

One Week Before — April 12th

| ✓ | TASK | NOTES |
| --- | --- | --- |
| ☐ | Charge all cameras — both SLR cameras to 100% |  |
| ☐ | Format and clear all memory cards |  |
| ☐ | Test QR code one final time on multiple devices |  |
| ☐ | Confirm load-in time with show organizer |  |
| ☐ | Pack all booth gear — camera, cables, laptop, decks, TV, signage |  |
| ☐ | Brief Christian on the full day — show him this document | Go through his script with him |
| ☐ | Confirm Instagram handle is current and profile is show-ready — bio, highlights, recent posts | Clean up if needed |
| ☐ | Set up lead follow-up sequence in DJEP — Templates 05 and 06 ready to send day after show |  |
| ☐ | Confirm Designer Weddings Victoria arrival and setup time at the show |  |

Day Before — April 18th

| ✓ | TASK | NOTES |
| --- | --- | --- |
| ☐ | Pack van — all booth gear loaded and organized |  |
| ☐ | Print final lead sheets and check all signage is packed |  |
| ☐ | Charge all devices — cameras, laptop, phone |  |
| ☐ | Set alarm for early departure |  |
| ☐ | Send Christian a reminder message with call time and his role sheet |  |
| ☐ | Review your show-day conversation flow one more time |  |

Show Day — April 19th

| ✓ | TASK | NOTES |
| --- | --- | --- |
| ☐ | Arrive at venue at load-in time — confirm with show organizer |  |
| ☐ | Coordinate backdrop setup with Designer Weddings Victoria |  |
| ☐ | Set up DJ booth, TV display, and all signage |  |
| ☐ | Set up lead capture station — QR code sign, clipboard, paper sheets |  |
| ☐ | Set up Instagram follow station — phone ready with profile open |  |
| ☐ | Test music at appropriate show volume |  |
| ☐ | Brief Christian on the day one final time — go through his script |  |
| ☐ | Doors open — Abraham DJs, Christian engages |  |
| ☐ | Track paper sign-ins throughout the day |  |
| ☐ | Post Instagram stories during the show — behind the scenes content |  |
| ☐ | Count and confirm all leads at end of show | Target: 20+ |
| ☐ | Pack down booth — leave venue clean |  |
| ☐ | Christian posts tagged photos within 2 hours of show end |  |

06 — PAPER LEAD CAPTURE SHEET

Print This — 50 Copies

Use this as the template for the paper backup sign-in sheet at the booth.

LEE ENTERTAINMENT Enter to Win — $1,500 Wedding Content Creation Package Winner announced May 1, 2026 · Fill in your details below

Your Name(s) _____________________________________________________________

Email Address _____________________________________________________________

Wedding Date _____________________________________________________________

Instagram Handle @

How did you hear about us? _____________________________________________________________

⭐ Also ask about our exclusive show offer — Free DJ booth decoration when you book before May 30th ⭐ abraham@leeentertainment.ca · vancouverislanddj.com

07 — POST-SHOW FOLLOW-UP PLAN

What Happens After the Show

The show is where you collect leads. The follow-up is where you convert them. Do not wait — speed is everything.

| TIMING | ACTION |
| --- | --- |
| Same day | Christian posts tagged couple photos on Instagram Stories and feed. Every person who followed gets tagged. |
| Within 24 hours | Enter all leads from paper sheets and QR code entries into DJEP. Send Template 05 (Wedding Show Lead — Initial Follow-Up) to every lead. |
| Day 4 | Send Template 06 (Wedding Show Lead — Day 4 Value Email) — "7 Questions to Ask Your DJ" to any lead that has not responded. |
| Day 10 | Send Template 06B follow-up to remaining unresponsive leads. |
| Day 21 | Send Template 06C final close to any remaining leads. |
| May 1 | Announce the $1,500 giveaway winner publicly on Instagram. Tag the winner. Post on Stories and feed. This generates more visibility and goodwill. |
| May 30 | Deadline for show-only booth decoration offer. Send a reminder to any leads who expressed interest but have not booked. |

LEE ENTERTAINMENT · CAKE & CHAMPAGNE SHOW PREP KIT · APRIL 19, 2026 · CONFIDENTIAL